## WBD - Calibration
| Frontend |  | Backend |  | Data |  | Other/Shared |  | Total
Use cases
Setup Activities |  | 0 |  | 0 |  | 0 |  | 0 | 0
| (ON HOLD) setup electron + setup react/electron IPC |  | Investigate + Setup Backend REST Framework (ASP.NET + routing + (+ ?) required for hosting REST services. |  | (ON HOLD) Setup Local SQL Server (Standard installation or docker?)
| (ON HOLD) Investigate + Setup Authentication mechanism |  | Investigate + Setup (Local) Hosting Environment (Self hosted / IIS / Docker / ..)
| Investigate + Setup Frontend (setup React framework + hot statefull reload + initial shared master UI (should we use a boilerplate?)) |  | Setup DI
| Investigate + Setup UI Framework (UI Fabric?) |  | Setup Logging
| Investigate + Setup Routing (navigation between screens, react-router?) |  | Setup NSWag (api documentation & nswag.json)
| Investigate + Setup State management (redux?) |  | (ON HOLD) Investigate + Setup Authentication mechanism
| Setup application bundler (build) (webpack) |  | Create REST interface guidelines (singular/plural resource names, default url, request, response format / query parameters etc.for GET, POST, PUT, DELETE)
| Setup Build server |  | Setup Build Server
Investigate + setup DI (if needed)
Setup automatic generation of NSWag REST client
Apply Thermo Fisher Style Guide
Investigate + Setup internationalization (i18n)
Select Qualities |  | 0 |  | 0 |  | 0 |  | 0 | 0
| Worklfow (multi-step) Framework (Routing to steps (URL or Global State?) + step tree UI, support for multiple iterations per step/substep) |  | REST interface + DTO's |  | Update Toucan Database Model
| Step Screen (UI + State + REST calls) |  | Data layer |  | Update DB Migration scripts (Carl => Toucan)
| Testing |  | Mock Data
Domain Model
Business Logic
Workflow steps interface definition (interface for defining the steps within a workflow)
Testing
Modify Lines & Parameters |  | 0 |  | 0 |  | 0 |  | 0 | 0
| Step Screen (UI + State + REST calls) |  | REST interface + DTO's |  | Update Toucan Database Model
| Testing |  | Data layer |  | Update DB Migration scripts (Carl => Toucan)
Mock Data
Domain Model
Business Logic
Testing
Export lines to Oxsas |  | 0 |  | 0 |  | 0 |  | 0 | 0
| Step Screen (UI + State + REST calls) |  | REST interface + DTO's |  | Update Toucan Database Model |  | Design Interface documentation for sending knowledge to Oxsas
| Oxsas Exporter (Models + Helper) |  | Data layer |  | Update DB Migration scripts (Carl => Toucan)
| Testing |  | Mock Data
Oxsas Exporter (Model + Helper)
Domain Model
Business Logic
Testing
Import Measurements |  | 0 |  | 0 |  | 0 |  | 0 | 0
| Step Screen (UI + State + REST calls) |  | REST interface + DTO's |  | Update Toucan Database Model |  | Design Interface documentation for importing measurements from Oxsas
| Oxsas Importer (Models + Helper) |  | Data layer |  | Update DB Migration scripts (Carl => Toucan)
| Testing |  | Mock Data
Domain Model
Business Logic
Testing
QA/CA: Numerical Presentation |  | 0 |  | 0 |  | 0 |  | 0 | 0
| Step Screen (UI + State + REST calls) |  | REST interface + DTO's |  | Update Toucan Database Model
| Testing |  | Data layer (mock if data model is not ready yet?) |  | Update DB Migration scripts (Carl => Toucan)
Domain Model
Business Logic
Domain specific MVR Helper
Testing
QA/CA: Graphical Presentation |  | 0 |  | 0 |  | 0 |  | 0 | 0
Side-menu & Header are already done in 'Numerical Presentation' | Investigate Charting libraries |  | REST interface + DTO's |  | Update Toucan Database Model
| Step Screen (UI + State + REST calls) |  | Data layer (mock if data model is not ready yet?) |  | Update DB Migration scripts (Carl => Toucan)
| Testing |  | Domain Model
Business Logic
Testing
Export Calibration to Oxsas |  | 0 |  | 0 |  | 0 |  | 0 | 0
| Step Screen (UI + State + REST calls) |  | REST interface + DTO's |  | Update Toucan Database Model |  | Design Interface documentation for sending calibration to Oxsas
| Oxsas Exporter (Models + Helper) |  | Data layer |  | Update DB Migration scripts (Carl => Toucan)
| Testing |  | Mock Data
Oxsas Exporter (Model + Helper)
Domain Model
Business Logic
Testing
[7 empty] | Total: |  | 0